## Slide 1
New Facilities Onboarding
AGLIPAY STP • HTT STP • EASTBAY PH-2 TP • KAYSAKAT TP
July 25, 2026
Source: O&M Manual Governance module • July 25, 2026
1 / 4
Notes: Executive title slide

## Slide 2
Governance Overview
Chart: 
| 1/25 | 2/25 | 3/25 | 4/25 | 5/25 | 6/25 | 7/25 | 8/25 | 9/25 | 10/25 | 11/25 | 12/25
Planned | 11 | 22 | 33 | 33 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Actual | 11 | 22 | 33 | 33 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44
Portfolio Summary
Current Planned: 40%
Current Actual: 44%
Variance: +4%
Status: On Track
Source: O&M Manual Governance module • July 25, 2026
2 / 4
Notes: Consolidated S-curve with actual line chart

## Slide 3
Facility Progress Overview
AGLIPAY STP
Planned
40.0%
Actual
44.0%
40% planned | 44% actual
On Track (+4%)
HTT STP
Planned
44.0%
Actual
44.0%
44% planned | 44% actual
On Track (0%)
EASTBAY PH-2 TP
Planned
22.0%
Actual
11.0%
22% planned | 11% actual
Delayed (-11%)
KAYSAKAT TP
Planned
11.0%
Actual
11.0%
11% planned | 11% actual
On Track (0%)
Source: O&M Manual Governance module • July 25, 2026
3 / 4
Notes: Four facility S-curves in 2x2 grid

## Slide 4
Deliverables Compliance Summary
Facility Deliverables Status
Facility | Required | Submitted | Approved | Missing | Compliance | Status
AGLIPAY STP | 14 | 3 | 3 | 11 | 21.4% | At Risk
HTT STP | 14 | 11 | 11 | 3 | 78.6% | In Progress
EASTBAY PH-2 TP | 14 | 4 | 4 | 10 | 28.6% | At Risk
KAYSAKAT TP | 14 | 1 | 1 | 13 | 7.1% | At Risk
Source: O&M Manual Governance module • July 25, 2026
4 / 4
Notes: Deliverables compliance matrix