## Slide 1
Portfolio PPP Status
2 facilities in PPP execution; 2 in pre-PPP readiness | July 31, 2026
PRE-PPP • Commissioning
PPP • Execution
POST-PPP • Sustainment
M1
T&C Complete
M2
Commissioning
M3
Punchlist Closed
M4
PM Setup
M5
PM Execution
M6
Training
M7
Optimization
M8
SLA Active
M9
BAU Ready
AGLIPAY STP
PPP ACTIVE
PPP START MAR 13, 2026
✓
✓
✓
○
✓
○
○
○
○
AGLIPAY: Active PPP with 0% documentation compliance; immediate recovery required.
HTT STP
PPP ACTIVE
PPP START MAR 13, 2026
✓
✓
✓
○
✓
○
○
○
○
HTT: Active PPP with 79% documentation compliance.
EASTBAY PH-2 TP
PRE-PPP • IN PROGRESS
PPP START SEP 01, 2026
✓
✓
✓
○
○
○
○
○
○
EASTBAY: Pre-PPP readiness at 29% documentation compliance.
KAYSAKAT TP
PRE-PPP • IN PROGRESS
PPP START SEP 01, 2026
✓
○
○
○
○
○
○
○
○
KAYSAKAT: Pre-PPP readiness at 7% documentation compliance.
✓
Completed
✓
Ahead
⚠
Delayed
○
Upcoming
NEXT GATE
Next Gate: PM Setup for AGLIPAY and HTT | Status: On Schedule

## Slide 2
Current PPP Position by Facility
PPP Progress from Start Date to Today | July 31, 2026
PRE-PPP
Commissioning
PPP
Execution
POST-PPP
Sustainment
JUL 2025
JAN 2026
JUL 2026
JAN 2027
JUL 2027
JAN 2028
MAY 2028
TODAY
31 JUL 2026
Legend
= PPP Period
= PPP Start
AGLIPAY STP
PPP: MAR 2026
PPP ACTIVE
4/9 milestones
HTT STP
PPP: MAR 2026
PPP ACTIVE
4/9 milestones
EASTBAY PH-2 TP
PPP: SEP 2026
PRE-PPP IN PROGRESS
3/9 milestones
KAYSAKAT TP
PPP: SEP 2026
PRE-PPP IN PROGRESS
1/9 milestones
EASTBAY and KAYSAKAT must complete pre-PPP readiness before their September 2026 PPP start.
Sources: O&M Manual Governance module

## Slide 3
Documentation Readiness
Final acceptance requires a fully compliant O&M Manual under the Standard Governance Framework
Sources: O&M Manual Governance module
PORTFOLIO READINESS
34%
19 of 56 Deliverables Complete
✓ Approved | — Missing
Facility Compliance
AGLIPAY STP
21%
HTT STP
79%
EASTBAY PH-2 TP
29%
KAYSAKAT TP
7%
Governance TOC Submission Matrix
TOC | AGLIPAY STP | HTT STP | EASTBAY PH-2 TP | KAYSAKAT TP
1 | ✓ | ✓ | ✓ | ✓
2 | — | ✓ | ✓ | —
3 | ✓ | ✓ | ✓ | —
4 | ✓ | ✓ | ✓ | —
5 | — | ✓ | — | —
6 | — | ✓ | — | —
7 | — | ✓ | — | —
TOC | AGLIPAY STP | HTT STP | EASTBAY PH-2 TP | KAYSAKAT TP
8 | — | ✓ | — | —
9 | — | ✓ | — | —
10 | — | ✓ | — | —
11 | — | ✓ | — | —
12 | — | — | — | —
13 | — | — | — | —
14 | — | — | — | —
EXECUTIVE OBSERVATION
Documentation submission ongoing across all facilities.