## Slide 1
AGLIPAY STP is in PPP execution
Milestone progress versus the sequence planned from each facility's PPP start date | Red marker = TODAY July 30, 2026
PRE-PPP • Commissioning readiness
PPP • Execution and capability
POST-PPP • Sustainment and BAU
M1
T&C
check
sheets
complete
M2
Wet/dry
commissioning
passed
M3
Defects
and
punchlist
closed
M4
PM
task
lists
in
SAP-PM
M5
PM/PdM
execution
started
M6
Training
completed
M7
Plan
refined
using
PPP
learnings
M8
Contracts
and
SLAs
activated
M9
BAU
governance
established
AGLIPAY STP
PPP ACTIVE
PPP START MAR 13, 2025
✓
✓
✓
✓
AGLIPAY Sewage Treatment Plant is critical path.
HTT STP
PPP ACTIVE
PPP START MAR 13, 2025
✓
✓
✓
✓
HTT Sewage Treatment Plant is critical path.
EASTBAY PH-2 TP
PPP ACTIVE
PPP START SEP 01, 2026
✓
✓
✓
EASTBAY Phase 2 Treatment Plant is critical path.
KAYSAKAT TP
PRE-PPP • IN PROGRESS
PPP START SEP 01, 2026
✓
KAYSAKAT Treatment Plant is critical path.
✓ Achieved as planned ✓ Achieved ahead of plan ! Planned by now—still open ✓ Upcoming milestone
NEXT GATE
All facilities progressing through governance milestones

## Slide 2
Today's position is explicit against every facility's PPP start date
Calendar-based phase timeline | July 30, 2026
PRE-PPP
Commissioning readiness
PPP
Execution and capability
POST-PPP
Sustainment and BAU
JUL 2025
JAN 2026
JUL 2026
JAN 2027
JUL 2027
JAN 2028
MAY 2028
TODAY • JUL 30, 2026
AGLIPAY STP
TODAY: PPP ACTIVE
PPP START • MAR 13, 2025
HTT STP
TODAY: PPP ACTIVE
PPP START • MAR 13, 2025
EASTBAY PH-2 TP
TODAY: PPP ACTIVE
PPP START • SEP 1, 2026
KAYSAKAT TP
TODAY: PRE-PPP • IN PROGRESS
PPP START • SEP 1, 2026
GATE IMPLICATION
Complete Pre-PPP milestones before gate.

## Slide 3
Documentation readiness is 13%; significant gaps remain
Final acceptance requires a fully compliant O&M Manual under the Standard Governance Framework
Sources: O&M Manual Governance module • IOM dated Jul 30, 2026
✓ Submitted = at least one uploaded document for the TOC row | — Missing = no submitted documents
TOC | AGLIPAY STP | HTT STP | EASTBAY PH-2 TP | KAYSAKAT TP
1 | — | — | — | —
1A | — | — | — | —
1C | — | — | — | —
2 | — | — | — | —
3 | — | — | — | —
4 | — | — | — | —
5 | — | — | — | —
6 | — | — | — | —
7 | — | — | — | —
8 | — | — | — | —
9 | — | — | — | —
10 | — | — | — | —
11 | — | — | — | —
12 | — | — | — | —
13 | — | — | — | —
14 | — | — | — | —
PORTFOLIO
8 / 64 • 13%
AGLIPAY STP
0 / 16 • 0%
HTT STP
3 / 16 • 19%
EASTBAY PH-2 TP
4 / 16 • 25%
KAYSAKAT TP
1 / 16 • 6%
EXECUTIVE OBSERVATION
AGLIPAY Sewage Treatment Plant requires acceleration.