## Slide 1
O&M Manual Governance
Executive Onboarding Progress
As of Jul 25, 2026
Generated: Jul 25, 2026, 11:58 PM
1 / 3
4
Onboarding Facilities
38%
Portfolio Progress
44%
Submission Coverage Proxy
36
Required Submissions — Proxy
16
Total Submitted
20
Outstanding — Proxy
Facility | Progress | Coverage | Required | Submitted | Outstanding | Status
Laguna | 75% | 89% | 9 | 8 | 1 | GREEN
Clark | 45% | 56% | 9 | 5 | 4 | AMBER
Tagum | 30% | 33% | 9 | 3 | 6 | RED
Estate | 0% | 0% | 9 | 0 | 9 | NO BASELINE
Submission coverage is based on a milestone-count proxy. Formal document approval workflow and a facility-specific deliverable requirement matrix are not currently available.
Notes: Executive dashboard with submission coverage proxy metrics.

## Slide 2
Facility S-Curve Analysis
Planned vs Actual Progress by Facility
As of Jul 25, 2026
Generated: Jul 25, 2026, 11:58 PM
2 / 3
Laguna
Actual: 75%
Planned: 72%
Variance: -3%
Coverage: 89%
8/9 submitted
Clark
Actual: 45%
Planned: 23%
Variance: -22%
Coverage: 56%
5/9 submitted
Tagum
Actual: 30%
Planned: N/A
Variance: N/A
Coverage: 33%
3/9 submitted
Estate
Actual: 0%
Planned: N/A
Variance: N/A
Coverage: 0%
0/9 submitted
Notes: S-curve analysis showing planned vs actual progress for each facility.

## Slide 3
Submission Coverage Proxy Deliverable Compliance & Executive Actions Executive Actions
As of Jul 25, 2026
Generated: Jul 25, 2026, 11:58 PM
3 / 3
Document Submission Summary
Category | Submitted | Rate
TOC-01 | 5 | 100%
TOC-03 | 5 | 100%
TOC-04 | 3 | 100%
TOC-08 | 2 | 100%
TOC-02 | 1 | 100%
Executive Actions
Priority | Facility | Action | Due
CRITICAL | Clark | Address significant schedule variance... | Sep 1, 2025
Portfolio Risk Summary
1 facility(ies) materially behind schedule
Mitigation: Expedite document submissions and milestone completion
Insufficient baseline schedule data
Mitigation: Establish project baselines for accurate tracking
Report uses proxy data sources (see dataQuality flags)
Mitigation: Implement workflow status tracking and deliverable requirement matrix
Submission coverage is based on a milestone-count proxy. Formal document approval workflow and a facility-specific deliverable requirement matrix are not currently available.
Notes: Deliverables compliance status and required executive actions.