## Slide 1
Eastbay is gate-ready; Kaysakat must close two Pre-PPP milestones
Milestone progress versus the sequence planned from each facility’s PPP start date | Red marker = TODAY, 28 July 2026
PRE-PPP • Commissioning readiness
PPP • Execution and capability
POST-PPP • Sustainment and BAU
M1
T&C check sheets
complete
M2
Wet/dry
commissioning passed
M3
Defects and
punchlist closed
M4
PM task lists
in SAP-PM
M5
PM/PdM execution
started
M6
Training
completed
M7
Plan refined using
PPP learnings
M8
Contracts and
SLAs activated
M9
BAU governance
established
AGLIPAY STP
PPP ACTIVE
PPP START 13 MAR 2026
✓
✓
✓
!
✓
Execution started early; SAP-PM task lists remain the sequence gap.
HTT STP
PPP ACTIVE
PPP START 13 MAR 2026
✓
✓
✓
!
✓
Execution started early; close SAP-PM task lists and training documentation.
EASTBAY PH-2 TP
PRE-PPP • GATE READY
PPP START 01 SEP 2026
✓
✓
✓
All Pre-PPP milestones are complete; prepare the SAP-PM transition.
KAYSAKAT TP
PRE-PPP • RECOVERY
PPP START 01 SEP 2026
✓
!
!
Wet/dry commissioning and defect closure must finish before PPP.
✓
Achieved as planned
!
Planned by now—still open
✓
Achieved ahead of plan
Upcoming milestone
NEXT GATE
Kaysakat: complete Wet/Dry Commissioning and close the Defects/Punchlist before PPP. Aglipay and HTT: close the SAP-PM task-list gap.
Notes: [Sources]
- User-supplied facility dashboard screenshots dated 28 July 2026 for Eastbay PH-2 TP, Kaysakat TP, HTT STP and Aglipay STP.
- User-supplied portfolio implementation slide showing achieved milestones and document status.
- Milestone definitions: M1 T&C Check Sheets Complete; M2 Wet/Dry Commissioning Passed; M3 Defects/Punchlist Closed; M4 PM Task Lists in SAP-PM; M5 PM/PdM Execution Started; M6 Training Completed; M7 Plan Refined using PPP Learnings; M8 Contracts/SLA Activated; M9 BAU Governance Established.
- Planned-by-today interpretation uses the dashboard S-curves anchored to each PPP start date: Aglipay and HTT planned through M4; Eastbay planned through M2; Kaysakat planned through M3.
- Achieved milestones retained from the supplied portfolio slide: Aglipay M1, M2, M3, M5; HTT M1, M2, M3, M5; Eastbay M1, M2, M3; Kaysakat M1.

## Slide 2
Today’s position is explicit against every facility’s PPP start date
Calendar-based phase timeline | 28 July 2026
PRE-PPP
Commissioning readiness
PPP
Execution and capability
POST-PPP
Sustainment and BAU
JUL 2025
JAN 2026
JUL 2026
JAN 2027
JUL 2027
JAN 2028
MAY 2028
TODAY • 28 JUL 2026
AGLIPAY STP
TODAY: PPP ACTIVE
PPP START • 13 MAR 2026
HTT STP
TODAY: PPP ACTIVE
PPP START • 13 MAR 2026
EASTBAY PH-2 TP
TODAY: PRE-PPP • GATE READY
PPP START • 01 SEP 2026
KAYSAKAT TP
TODAY: PRE-PPP • RECOVERY
PPP START • 01 SEP 2026
GATE IMPLICATION
Kaysakat and Eastbay reach PPP on 01 September. Eastbay is ready; Kaysakat must close commissioning and defect milestones before the gate.
Notes: [Sources]
- User-supplied facility dashboard screenshots dated 28 July 2026.
- Aglipay and HTT PPP start: 13 March 2026.
- Eastbay PH-2 TP and Kaysakat TP PPP start: 1 September 2026.
- Phase windows follow the dashboard definition: Pre-PPP −8 to 0 months; PPP 0 to +12 months; Post-PPP +12 to +20 months.

## Slide 3
Documentation readiness is 34%; HTT carries the portfolio
Final acceptance requires a fully compliant O&M Manual under the Standard Governance Framework.
Sources: O&M Manual Governance module • IOM dated 07 Jan 2026 • 27 Jul 2026
✓ Submitted = at least one uploaded document for the TOC row | — Missing = no submitted document
Governance TOC section | AGLIPAY | HTT | EASTBAY | KAYSAKAT
01 Executive Summary | — Missing | ✓ Submitted | — Missing | — Missing
02 Facility Overview & Process Description | — Missing | ✓ Submitted | ✓ Submitted | — Missing
03 Operating Philosophy | — Missing | ✓ Submitted | — Missing | — Missing
04 Standard Operating Procedures (SOPs) | — Missing | ✓ Submitted | — Missing | — Missing
05 Standard Maintenance Procedures (SMPs) | — Missing | ✓ Submitted | — Missing | — Missing
06 Maintenance Management Framework | — Missing | ✓ Submitted | — Missing | — Missing
07 SCADA and Automation | — Missing | ✓ Submitted | ✓ Submitted | — Missing
08 Testing, Commissioning & Proving | ✓ Submitted | ✓ Submitted | ✓ Submitted | ✓ Submitted
09 As-Built Drawings & Final Technical Documentation | — Missing | — Missing | — Missing | — Missing
10 Training & Competency Records | — Missing | ✓ Submitted | — Missing | — Missing
11 Digital / SAP S/4HANA Onboarding | ✓ Submitted | ✓ Submitted | — Missing | — Missing
12 Critical Spares Handover | ✓ Submitted | ✓ Submitted | ✓ Submitted | — Missing
13 Acceptance & Handover | — Missing | — Missing | — Missing | — Missing
14 Facility-Specific Addenda | — Missing | — Missing | — Missing | — Missing
Approved / Required | 3 / 14 | 11 / 14 | 4 / 14 | 1 / 14
Compliance | 21% | 79% | 29% | 7%
EXECUTIVE OBSERVATION
HTT leads at 79%.
Eastbay is building submission momentum.
Accelerate Aglipay and Kaysakat before acceptance.
PORTFOLIO
19 / 56 • 34%
AGLIPAY STP
3 / 14 • 21%
HTT STP
11 / 14 • 79%
EASTBAY PH-2 TP
4 / 14 • 29%
KAYSAKAT TP
1 / 14 • 7%
Notes: [Sources]
User-provided O&M Manual Governance dashboard screenshots captured 26 July 2026.
User-provided Interoffice Memo: Standard O&M Manual Governance Framework, dated 7 January 2026.